## Sheet1
Reference Number | Task Name | Task Description | Deleverables | Duration (hrs) | People | Resources Needed | Dependecies | Dates (Approximate)
1 | Risk Assesment | Possible casue of malfunction, errors, no area coverage, breakage and overall durability | Broken/ Damaged parts | 2 | Victor | N/A | Required Model Parts | Nov 18th
|  |  | Chip malfunction | 2 | Angel | N/A | N/A
|  |  | Parts malfuction | 2 | Hetanshu | N/A | N/A
|  |  | Durability | 1 | Alana | Bus Stations | Weather
2 | Adviser Meeting | Discuss possible alterations and compatabality for parts | Modify design | 4 | Hetanshu | N/A | N/A | Dec 1st
3 | Assembly | Get started on the project/ construction | Solar Panels | 4 | Alana | Funds | N/A | Jan 13th
|  |  | Cost for each equipment | 4 | Victor | N/A | N/A
|  |  | Batteries | 4 | Hetanshu | Funds | N/A
|  |  | Locations | 4 | Angel | Bus stations | Bus stations
4 | Testing and Benchmarking | Test and make sure the design work as intended | Completed design | 4 | Victor | Sunlignt | Solar energy | Feb 13th
5 | Revision | Correct the mistakes and problems/ optamize it | Completed Design | 10 | Hetanshu | Data from previos stage | Data from previos stage | Feb 24th
Alana
Angle
6 | Final Design | Final design with details that include all the possible parts, their specification and purchasing cost | Solar Panels | 2 | Alana | Funds | N/A | Mar 13th
|  |  | Cost for each equipment | 2 | Victor | N/A | N/A
|  |  | Batteries | 2 | Hetanshu | Funds | N/A
|  |  | Locations | 2 | Angel | Bus stations | Bus stations
7 | Final Demo | Final completed model which functions as the customer needs. | Test | 3 | All team members | Sunny day | Sun | April 1st
|  |  | Presentation | 1 | All team members | N/A | N/A
7
8