## Sheet1
Reference Number | Task Name | Task Description | Deleverables | Duration (hrs) | People | Resources Needed | Dependecies
1 | Customer Needs | Meet the Adviser, Sponsor to discuess the project idea, concept,expecatation and final product | Interview | 2 | All team members,Sponsor, Adviser | N/A | N/A
|  |  | Team discussion | 1 | All team members | N/A | N/A
|  |  | Market Research | 4 | Hardware (Hetanshu) | N/A | N/A
[5 empty] | Software (Angel) | N/A | N/A
[5 empty] | Cost Planning (Victor) | N/A | N/A
[5 empty] | General Topic (Alana) | N/A | N/A
|  |  | Write a Document | 5 | Angle, Victor | N/A | N/A
|  |  | Proofread and revise | 1 | Hetanshu Patel | N/A | N/A
2 | Functional Decomposition | Solar panel unbrella which has capability of producing power for several potential uses | Functional Req | 3 | Angel | Based on Customer Needs | Based on Customer Needs
|  |  | Input Req |  | Victor | " | Based on Customer Needs
|  |  | Output Req |  | Hetanshu | " | Based on Customer Needs
|  |  | Functional Behavior |  | Alana | " | Based on Customer Needs
3 | Targets | Assigment deadlines on canvas, sponsor deadlines | Initial Meeting with Customer | 2 | All team members | N/A | N/A
|  |  | Proposing a Design | 1 | All team members | Micorsoft Viso | Based on Customer Needs
|  |  | Finalizing Design | 1 | Angel | Micorsoft Viso | Based on Customer Needs
|  |  | Order Parts | 4 | Victor | Funds from Sponsor | N/A
|  |  | Assambley | 15 | Hetanshu, Alana | Hardware assembling tools | Ordered Parts
|  |  | Programming | 6 | Angel, Victor | C++, Python, MATLAB, etc | Assambley
|  |  | Functions as intended | 1 | All team members | N/A | N/A
|  |  | Customer Satisfaction | 1 | All team members | N/A | Based on Customer Needs
|  |  | Finalize Model | 1 | All team members | N/A | Based on Customer Needs
4 | Concept Generation | Designs and ideas of the model based on customer needs and requirments | Internal Serach | 2 | All team members | N/A | N/A
|  |  | External Search | 2 | All team members | Literature search, review of patents | N/A
|  |  | Concept Table | 3 | All team members | N/A | N/A
|  |  | Initial Design | 4 | All team members | Micorsoft Viso | N/A
|  |  | Updates based on customer needs | 1 | All team members | Micorsoft Viso | Based on Customer Needs
|  |  | Final Product design | 2 | All team members | Micorsoft Viso | N/A
5 | Concept Selection | Fianlize the model based on design, parts, cost effiecient, reliable and other customer needs | Cost efficient | 1 | Alana | N/A | N/A
|  |  | Parts avilalibility | 1 | Victor | N/A | Market/ Product availability
|  |  | Reliability | 1 | Angel | N/A | N/A
|  |  | Achievable | 1 | Hetanshu | N/A | N/A
6 | Risk Assesment | Possible casue of malfunction, errors, no area coverage, breakage and overall durability | Broken/ Damaged parts | 2 | Victor | N/A | Required Model Parts
|  |  | Chip malfunction | 2 | Angel | N/A | N/A
|  |  | Parts malfuction | 2 | Hetanshu | N/A | N/A
|  |  | Durability | 1 | Alana | Bus Stations | Weather
7 | Detailed Design | Final design with details that include all the possible parts, their specification and purchasing cost | Motors | 2 | Hetanshu | Funds | N/A
|  |  | Solar Panels | 2 | Alana | Funds | N/A
|  |  | Pole | 2 | Alana | Funds | N/A
|  |  | Cost for each equipment | 2 | Victor | N/A | N/A
|  |  | Batteries | 2 | Hetanshu | Funds | N/A
|  |  | Locations | 2 | Angel | Bus stations | Bus stations
8 | Final Demo | Final completed model which functions as the customer needs. | Test | 3 | All team members | Sunny day | Sun
|  |  | Presentation | 1 | All team members | N/A | N/A